,

SimTech

CS 2340 – Fall 2004

M6: Final

OTIB OS Team

Jose Caban

Andrew Knight

Dung Nguyen

Vladimir Urazov

Table of Content

1	Team Roles and Responsibilities	1

2	Work Breakdown	1

2.1	Time Estimation	1

2.2	Task/Activity Breakdown	2

2.2.1	Milestone 1	2

2.2.2	Milestone 2	2

2.2.3	Milestone 3	2

2.2.4	Milestone 4	2

2.2.5	Milestone 5	3

2.2.6	Milestone 6	5

3	Risk Management	6

4	Test Plans	7

4.1	M4	7

4.2	M5	9

4.3	M6	9

# 1	Team Roles and Responsibilities

Project Manager and Design

Jose Caban

Jose will be in charge of planning the project, leading weekly meetings, and keeping up with communication between other members, supervising the project progress and managing risks.

Core Development and Design

Dung Nguyen

Dung will mainly be in charge of designing and implementing the back-end core of the game.  This includes interactions between person and person, person and item, person’s movements and objects’ arrangement in the world. He will also assist Jose in writing documents.

Core Development/Graphical System Development

Vladimir Urazov

Vladimir will be in charge of the entire user interface and graphical engine (a visual representation of the back-end).  He will also cooperate with Dung in coding and makes some dynamic diagrams of the simulator.

Test and QA Lead

Andrew Knight

Andrew will be in charge of taking the lead role in developing a deep and effective test suite including scenario tests. He also analyzes all requirements and ensuring the project is headed in the proper direction.

# 2	Work Breakdown

## 2.1	Time Estimation

Since we are working on a schedule constrained by both the milestone due dates and other classes, all durations are based on a scale for convenience.

- A scheduled duration of one day approximately equals between 1-4 hours

- During a period of 1 scheduled day, approximately 200 lines of code per person should be reasonable to complete.

- The completed Test Suite, including manual testing, should be capable of being run through in less than 2 scheduled days with all group members participating.

- Any written documentation can be written at a pace of 3 pages per work day per member.

These estimations are based on past experiences and educated guessing.  The estimated values and below durations will be adjusted accordingly as the project continues.

## 2.2	Task/Activity Breakdown

Since M1, M2, M3 have already passed, only M4 and up are described in this section.

### 2.2.1	Milestone 1

### 2.2.2	Milestone 2

### 2.2.3	Milestone 3

Milestone has passed and we did a better job than expected.  Our design is good enough that we did not have to make significant changes for M4.

### 2.2.4	Milestone 4

- T8 – M4 Requirement Analysis

  - Dependencies: T7

  - Duration: Friday, October 15, 2004 – Friday, October 15, 2004

  - Person in Charge: Whole team

  - Product: Good understanding on M4.

- T9 – Planning

  - Dependencies: T8

  - Duration: Saturday, October 16, 2004 – Sunday, October 17, 2004

  - Person in Charge: Jose Caban and Dung Nguyen

  - Product: Detailed document of what to be done (and upgrade of the document you are reading).

- T10 – Graphical Interface Proposal

  - Dependencies: T9

  - Duration: Monday, October 18, 2004 – Tuesday, October 19, 2004

  - Person in Charge: Vladimir Urazov

  - Product: A sketch of how the game looks like (i.e. how to represent each character), how a player interacts with the game (menu-based or direct manipulation).

- T11 – Graphical Interface Approval

  - Dependencies: T10

  - Duration: Wednesday, October 20, 2004 – Wednesday, October 20, 2004

  - Person in Charge: Whole team

  - Product: Comments on improving the interface. A final interface will be released on the same day.

- T12 – Adding Classes for the UI to UML Class Diagram

  - Dependencies: T11

  - Duration: Thursday, October 21, 2004 – Thursday, October 21, 2004

  - Person in Charge: Dung Nguyen

  - Product: Updated Class Diagram with classes for the interface.

- T13 – Drawing

  - Dependencies: T11

  - Duration: Thursday, October 21, 2004 – Thursday, October 21, 2004

  - Person in Charge: Vladimir Urazov

  - Product: All images needed (buttons, characters, etc).

- T14 – Developing UI

  - Dependencies: T12, T13

  - Duration: Friday, October 22, 2004 – Monday, October 25, 2004

  - Person in Charge: Vladimir Urazov (mainly) and all other members.

  - Product: All images needed (buttons, characters, etc).

- T15 – Demo to TA

  - Dependencies: T14

  - Duration: Tuesday, October 26, 2004 – Wednesday, October 27, 2004

  - Person in Charge: Jose Caban (mainly) and all other members.

  - Product: Suggestions from TA.

- T16 – Building Test Plan for UI

  - Dependencies: T15

  - Duration: Tuesday, October 26, 2004 – Wednesday, October 27, 2004

  - Person in Charge: Andrew Knight.

  - Product: A test plan for UI.

- T17 – Adjusting UI

  - Dependencies: T15

  - Duration: Thursday, October 28, 2004 – Thursday, October 28, 2004

  - Person in Charge: Vladimir Urazov.

  - Product: A new UI that satisfies TA’s suggestions.

- T18 – Interacting between UI and back-end

  - Dependencies: T17

  - Duration: Friday, October 29, 2004 – Sunday, October 31, 2004

  - Person in Charge: Vladimir Urazov, Dung Nguyen and Jose Caban.

  - Product: A version of the simulation with both UI and back-end.

- T19 – Building Test Plan for both UI and Back-end

  - Dependencies: T17

  - Duration: Friday, October 29, 2004 – Sunday, October 31, 2004

  - Person in Charge: Andrew Knight.

  - Product: A test plan for the new version of the simulation.

- T20 – Picking up Slack

  - Dependencies: T19

  - Duration: Monday, November 1, 2004 – Monday, November 1, 2004

  - Person in Charge: Jose Caban (mainly) and all other members.

  - Product: A turn in version for M4.

- T21 – Turning in

  - Dependencies: T20

  - Duration: Tuesday, November 2, 2004 – Tuesday, November 2, 2004

  - Person in Charge: Jose Caban.

  - Product: M4 up to Swiki.

### 2.2.5	Milestone 5

- T22 – Demo M4

  - Dependencies: T21

  - Duration: Wednesday, November 3, 2004 – Thursday, November 4, 2004

  - Person in Charge: Jose Caban and Dung Nguyen.

  - Product: Grades for M4 and suggestions for M5.

- T23 – Technical Training

  - Dependencies: T22

  - Duration: Friday, November 5, 2004 – Saturday, November 6, 2004

  - Person in Charge: All members.

  - Product: Knowledge about Morphic, Wonderland.

- T24 – M5 Requirement Analysis

  - Dependencies: T23

  - Duration: Sunday, November 7, 2004 – Sunday, November 7, 2004

  - Person in Charge: All members.

  - Product: Good understand about M5.

- T25 – M5 Planning

  - Dependencies: T24

  - Duration: Monday, November 8, 2004 – Monday, November 8, 2004

  - Person in Charge: Jose Caban.

  - Product: An update schedule for M5 (who do what and when).

- T26 – Adding Time-step to Characters

  - Dependencies: T25

  - Duration: Tuesday, November 9, 2004 – Wednesday, November 10, 2004

  - Person in Charge: Dung Nguyen and Vladimir Urazov.

  - Product: Characters will have the ability to fire some random actions by himself.

- T27 – Test Plan for Time-step Feature

  - Dependencies: T25

  - Duration: Tuesday, November 9, 2004 – Wednesday, November 10, 2004

  - Person in Charge: Andrew Knight.

  - Product: Test Plan for Time-step feature.

- T28 – Adding Random Actions to Characters

  - Dependencies: T26, T27

  - Duration: Thursday, November 11, 2004 – Saturday, November 13, 2004

  - Person in Charge: Dung Nguyen and Vladimir Urazov.

  - Product: Set of random actions that a character can do.

- T29 – Picking up Slack

  - Dependencies: T28

  - Duration: Sunday, November 14, 2004 – Monday, November 15, 2004

  - Person in Charge: Jose Caban (mainly) and other members.

  - Product: A perfect version for turning in.

- T30 – Turning in

  - Dependencies: T29

  - Duration: Tuesday, November 16, 2004 – Tuesday, November 16, 2004

  - Person in Charge: Jose Caban.

  - Product: M6 up to Swiki.

### Milestone 6

Up to this point, we should have everything required done. All left are to create data to run the game (i.e. add more buildings, rooms) and save/load game, which are easy to do with our design. We will meet more often to do exhausted testing and have some fun with the game.  There is no intention to do multiple players at the moment, but depends on how well we do on M3-M5, we might give this some thought.

- T31 – Demo M5

  - Dependencies: T30

  - Duration: Wednesday, November 17, 2004 – Thursday, November 18, 2004

  - Person in Charge: Jose Caban and Dung Nguyen.

  - Product: Grade for M5 and feedbacks and suggestions form M6 from TA.

- T32 – M6 Requirement Analysis

  - Dependencies: T31

  - Duration: Friday, November 19, 2004 – Friday, November 19, 2004

  - Person in Charge: Jose Caban (mainly) and all other members.

  - Product: Good understand about M6.

- T33 – Planning

  - Dependencies: T32

  - Duration: Saturday, November 20, 2004 – Saturday, November 20, 2004

  - Person in Charge: Jose Caban.

  - Product: An update plan for M6.

- T34 – Adding Buildings

  - Dependencies: T33

  - Duration: Sunday, November 21, 2004 – Sunday, November 21, 2004

  - Person in Charge: Dung Nguyen and Vladimir Urazov.

  - Product: A world with some buildings.

- T35 – Building Test Plan for Adding Buildings

  - Dependencies: T33

  - Duration: Sunday, November 21, 2004 – Sunday, November 21, 2004

  - Person in Charge: Andrew Knight.

  - Product: Test cases to see if all buildings are added properly.

- T36 – Adding Rooms

  - Dependencies: T33, T34

  - Duration: Monday, November 22, 2004 – Monday, November 22, 2004

  - Person in Charge: Dung Nguyen and Vladimir Urazov.

  - Product: Buildings have rooms.

- T37 – Test Cases for Adding Rooms

  - Dependencies: T33, T34

  - Duration: Monday, November 22, 2004 – Monday, November 22, 2004

  - Person in Charge: Andrew Knight.

  - Product: Test cases to see if all rooms are added properly.

- T38 – Adding Persons and Furniture

  - Dependencies: T36, T37

  - Duration: Tuesday, November 23, 2004 – Wednesday, November 24, 2004

  - Person in Charge: Dung Nguyen and Vladimir Urazov.

  - Product: Rooms have persons and furniture.

- T39 – Test cases for Adding Persons and Furniture

  - Dependencies: T36, T37

  - Duration: Tuesday, November 23, 2004 – Wednesday, November 24, 2004

  - Person in Charge: Andrew.

  - Product: Rooms have persons and furniture.

- T40 – Adding Loading and Saving Features

  - Dependencies: T38, T39

  - Duration: Thursday, November 25, 2004 – Thursday, November 25, 2004

  - Person in Charge: Dung Nguyen and Vladimir Urazov.

  - Product: Rooms have persons and furniture.

- T41 – Intensive Testing

  - Dependencies: T40

  - Duration: Friday, November 26, 2004 – Wednesday, December 01, 2004

  - Person in Charge: All team members.

  - Product: Final version.

- T42 – Turn in

  - Dependencies: T41

  - Duration: Thursday, December 02, 2004 – Thursday, December 02, 2004

  - Person in Charge: Jose Caban.

  - Product: Final version up to Swiki.

# 3	Risk Management

We believe that there will be risks for this project because of few reasons:

  - Some requirements are not well-defined.

  - We are not Squeak-gods, which leads to many technical difficulties later.

  - Some unforeseen circumstances.

To minimize affects of risks, we have Jose supervising the whole project. He will figure out what goes wrong, who does it and response to that properly (i.e. a member stops working, CVS down, etc).  For the quality of code, we dedicate Andrew to build test plans for the entire game as well as test cases for function.  He will be the first one to know if the code work as expected or the game operates as planned.

The biggest risk might happen with the back-end which is been in charge by Dung.  Affects of this risk might not be easy to figure out since everything happen in the back.  To minimize the affects, we have Andrew building test cases to make sure that Dung is on the right track.  We also have Vladimir, who is in charge of UI and graphical representation, working close to Dung to create visual tests for the back-end.

There might be a lot of bugs in the UI and graphical representation, however, these bugs should be easy to discover since everything is visual.  With Vladimir’s skills, they will be fixed in no time.

# 4	Test Plans

As M1, M2 have already passed, we will not include test plans for these two milestones in this document. Also, since M3 is only about designing, there is no test plans for this milestone either.  Last note, we have not started M4-M6, so we will not answer the question “What is the actual result when you test your program before turning in”.

## M4

| Item # | Context | Test | Expected Result | Actual Result |
| --- | --- | --- | --- | --- |
| 1 | A game is in process. | Create a new person (let’s call him John) with no attribute, factor and put him to a room (let’s assume it is TA Lab). | View switched to TA Lab and John should be there. Factors of people in the room should not be changed. | View does switch to TA Lab and John is here. No factor is changed. |
| 2 | View is set to TA lab. | Create a radio with no factor and add it to the room | The radio should appear in TA Lab. Factors of people in the room should not be changed. | The radio does appear in TA Lab and nobody is affected by its appearance. |
| 3 | View is set to TA lab and John is here. | Choose John | A dialog should pop up showing John’s information. There should not be any information about John’s factors because he does not have one | Information about John appears in a yellow window on the up right corner. He does not have any factor. |
| 4 | Current person is John. | Add funniness attribute to John and set it to 4. | John’s funniness attribute should be 4. Happiness factor of people in TA Lab should increase by 4. | John now has attribute funniness and it is 4. Happiness factor of people in TA Lab increases by 4. |
| 5 | Current person is John. | Increase John’s funniness attribute to 5. | John’s funniness attribute should be 5. Happiness factor of people in TA Lab should increase by 1. | John now has attribute funniness and it is 5. Happiness factor of people in TA Lab increases by 1. |
| 6 | View is set to TA lab and the TV is here. | Choose the radio | A dialog should pop up showing the radio’s information. There should not be any information about radio’s factors because it does not have one | A dialog should pop up showing all information about the radio, including all actions that the radio can do (play, stop). |
| 7 | TV in TA Lab is selected. | Add entertaining attribute to the radio and set it to 3 | The radio’s entertaining attribute should be 3. Sleepiness factor of people in TA Lab should decrease by 3. | The radio has an entertaining attribute and it is 3. Sleepiness factor of people in TA Lab decreases by 3. |
| 8 | TV in TA Lab is selected. | Decrease the TV’s entertaining attribute to 2. | The TV’s entertaining attribute should be 2. Sleepiness factor of people in TA Lab should increase by 1. | The radio’s entertaining attribute is 2. Sleepiness factor of people in TA Lab increases by 1. |
| 9 | View is set to TA Lab | Add a book which has sleepiness attribute equals to 2 to the room. Add sleepiness factor to John and set it to 10. Order John to pick the book up. | The book should disappear from TA Lab. It should appear in John’s list of items. John’s sleepiness factor should be 12 | The book does disappear from TA Lab. John is now carrying the item. His sleepiness factor is 12. |
| 10 | View is set to TA Lab | Order John to drop the book. | The book should disappear from John’s list of items. It should appear in TA Lab. John’s sleepiness factor should be 10. | John no longer carries the book. It appears again in TA Lab. John’s sleepiness factor is 10. |
| 11 | View is set to TA Lab and there are some persons in the room, one of them is John. | Order John to go to the next room (States Cluster). | John should disappear for TA Lab. Change view to States Cluster, John should be seen here. | John change his location to States Cluster. |
| 12 | View is set to States Cluster and there are some persons in the room, one of them is John. | Add Puyan with craziness attribute equals to 2 to the room and order him to talk to John. | John’s happiness factor should decrease by 2. | John’s happiness factor decreases by 2. |
| 13 | A game is in process | Save game to “mygame.sav” | mygame.sav appears in the current folder. | mygame.sav does appear in the current folder. |
| 14 | A game is in process | Load game from “mygame.sav” | The current game stops, the saved game starts. | The current game stops and the saved game starts (only one instance of the game running) |

* Note: Some tests were executed from the workspace.

## 4.2	M5

| Item # | Context | Test | Expected Result |
| --- | --- | --- | --- |
| 15 | Simulation mode off. | All tests for M4 | Like M4 |
| 16 | Simulation mode on and view is set to States Cluster | Add a “desire to pick up stuff” to John. Set the frequency of the action to once every 2 s (in real life) and probability that the action happens to 50%. | After 10 s waiting, John should pick up something in the room. |
| 17 | Simulation mode on and view is set to States Cluster | Add a “desire to talk to people” to John. Set the frequency of the action to once every 5 s (in real life) and probability that the action happens to 75%. | After 20 s waiting, John should approach somebody in the room. |
| 18 | Simulation mode on and view is set to States Cluster | Add a “desire to move” to John. Set the frequency to move to once every 10 s (in real life) and probability to move to 90%. | After 30 s waiting, John should move to another room. |

## 4.3	M6

In our design, Room and Building are actually the same (they are both Location), so all the functionalities work with Room should work with building. Therefore, there is no test plan for Building.

| Item # | Context | Test | Expected Result | Actual Result |
| --- | --- | --- | --- | --- |
| 19 | A game is in process. There are 3 buildings: CoC (which has States Cluster & TA Lab), Physics (which has L1 & L2 lecture rooms) and Student Center (which has a cafeteria and game room). | Player chooses to save the world to 1.world | 1.world should be created. The file will be in XML format: <building name = CoC> <room name = TA Lab> ..... </room> </building> | Files are not in XML format but are rather saved as binaries. Saving works the same as before since everything is just a location. |
| 20 | The very first screen of the application. | Player chooses to load 1.world | The loaded World should have all elements stated in Item 17s’ Context. | The initial screen was not implemented due to time constraints and its worthlessness. |
| 21 | Like 17 with extra details: there is John (sleepiness = 10) in TA Lab, Puyan (craziness = 30) in States Cluster, Jose (hungriness =70) in Student Center). | Player chooses to save the world to 1.person | 1.world should be created. The file will be in XML format: <person name = John> <room name = TA Labs> .... </room> </person> | As expected but as a binary. |
| 22 | 1.world has been loaded. | Player chooses to load 1.person | The loaded World should have all elements stated in Item 19s’ Context. | As expected. |